## Project Details
Project Name: | Niftem
Module Name: | System Testing
Tested By: | Prashant Sharma
Developed By: | Beena/Shivali

## Dev_Server
Sr .No | Scenario Name | Steps | Input Data/Browsers | Actual Results | Status (Pass/Fail) | Start Date | End Date | Dev Comment
1 | Verify that Log in | 1. Go to: http://niftemfeb.businesstowork.com/ 2. Enter the “Email ID”. 3. Enter the “Password”. 4. Click on “Log in” button. 5. Verify that user log in Successful or not. 6. Verify that alignment is proper or not. 7. Verify spellings are correct or not. 8. Verify that UI messages are proper displaying or not. 9. Verify that all functionality is working properly or not. | Valid Data:- User Name: admin PW: 123 Invalid Data:- 1.User Name:-”dsd<GFSDGSDFGSDFG>” PW: 123 2.User Name:-”admin” PW: “dsd<GFSDGSDFGSDFG>” | 1. No Validation For Blank Field. 2. No Validation for Email ID. 3. If I click on Submit button without Enter the data then No UI Message is displaying. 4. If I Enter the Invalid data and click on submit button then Error page is coming. Please refer SS1. 5. Text box character length is not fixed. 6.When I enter valid user id and invalid Password, then it displays error message as “Please enter correct email address instead of displaying an error message as “ Please enter correct Password”. | Fail | 28/04/2016 | 28/04/2016 | 1.Done 2.Done 3.Done 4.Done 5.Done
2 | Verify the Home Page | 1. Go to: http://niftemfeb.businesstowork.com/ 2. Log in With Valid Credential. 3. Verify that alignment is proper or not. 4. Verify spellings are correct or not. 5. Verify that UI messages are proper displaying or not. 6. Verify that all functionality is working properly or not. | Valid Data:- User Name: admin PW: 123 | 1. Log out Text is not proper visible. Please refer SS2 2. Log out Alignment is not proper. 3. When I click on Logo Icon then Page should be redirect to home page. | Fail | 28/04/2016 | 28/04/2016 | 1.Done 2.Done 3.Done
3 | Verify the Create All Admin | 1. Go to: http://niftemfeb.businesstowork.com/ 2. Log in With Valid Credential. 3. Click on “Administrative” Tab. 4. Select the “Create All Admin”. 5. Enter the details & Click on “Add Record” button. 6. Verify that Record added Successfully or not. 7. Verify that alignment is proper or not. 8. Verify spellings are correct or not. 9. Verify that UI messages are proper displaying or not. 10. Verify that all functionality is working properly or not. | Valid Data:- User Name: admin PW: 123 | 1. After session expire login page is opening current page. Please refer SS3. 2. Text box Length(Character Limit) are not define. 3. Page Title is not proper define. 4. No Validation on Email Field. 5. Validation Message is not proper. Please refer SS4 6.Text Name Should be “Admin User” instead of “User Department”. Please refer SS5 7. PF number is accepting the numeric Value but there are no validation when I am entering the Character. (but PF number is not submitting when I enter the character and its a Mandatory field.) 8. “Close” button is not working. 9. When I click on update button then data is updating but Field is not reset. 10. if I Enter the more then 9 digit in PF number the PF number is not saved and I got the message “Save successfully” . 11. Paging is not define. 12 .When I Enter the duplicate Record then I get the message “True”. 13. “PF Number” Need to written in single line. 14. Text box alignment is not proper. For Point 12 to 14 Please refer SS6. 15. Page Title Name is not proper define. | Fail | 28/04/2016 | 28/04/2016 | 2.Done 3.Done 4.Done 5.Done 6.Done 7.Done 8.Done 9.Done 10.Done 13.Done 14.Done 15.Done
4 | Verify the Assign Right | 1. Go to: http://niftemfeb.businesstowork.com/ 2. Log in With Valid Credential. 3. Click on “Administrative” Tab. 4. Select the “Assign Right”. 5. Enter the details & Click on “Add Record” button. 6. Verify that Record added Successfully or not. 7. Verify that alignment is proper or not. 8. Verify spellings are correct or not. 9. Verify that UI messages are proper displaying or not. 10. Verify that all functionality is working properly or not. | Valid Data:- User Name: admin PW: 123 | 1. When I click on “Save” button without select “admin” then Error page is coming. Please refer SS7 2. Right Functionality is not working properly.(eg: User admin should not be able to change the super admin rights) . 3. “Information center” is mentioned twice in the table. 4. “Id” is not properly defined. For Point 3 & 4 Please refer SS8 5. Page title is not proper define. Please refer SS9 6. When I create the log in then it mention as Name but when I assign the rights then its mention user name. | Fail | 28/04/2016 | 2016-02-05
SS4
SS7
SS8
SS9