## Sheet1
Major Contracts / POs Completion Status
Up to June 30, 2007.
Tender Number | Item / Nature of work | Contract Number | Contract date | Name of contractor | Scheduled start date | Actual date of start of work | Scheduled completion date | Actual completion date | Reasons for delay
RRFQ/004099/MPS | Mech works | 4300000708 | 2005-09-07 | Hazarika & Co. | 22/.8/2005 | 22/08/2005 | 21/01/2006 | 2007-12-06 | Site hold up due to delay in completing RCC OH tank
Tender floated by M/s BPCL | Construction of RO at Khampur, NH-1 | 4300000701 | 2005-07-09 | Shashi Construction | 2005-09-02 | 2005-09-02 | 2005-08-05 | 2006-03-04 | 1. Delay in receipt of 70KL & 20 KL tanks, 2. Shifting of HT electric pole delayed const. of approach road.
NRL/RO/04-05/010 | Civi/Elec/Mecha works in Makum, Sivasagar, Amoni | 4300000705 | 2005-07-09 | D. P. Enterprise | 2005-10-02 | 15/2/2005 | 31/11/2005 | 24/6/2006 | Phasewise site handed over for 3 Dealer controlled Ros, const. of which were in dealer's scope.
NRL/RO/05-06/017 | Construction of Retail outlet at Jorabat | 4300001230 | 24/10/2005 | Tirupati Construction Co. | 29/7/2005 | 29/7/2005 | 15/12/2005 | 14/1/2006 | Balance hillock cutting & stone blasting was not done by the dealer.
Col No. LC05000002 | Supply of HCL, 30% concentration | 5500000003 | 25.10.2005 | Sunil Chemicals | 25/10/2005 | 28/10/2005 | 25/10/2006 | 19/07/2006 | Delivery schedule issued depending upon requirement based on actual consumption of chemical
NRL/COMM(PUR)/GSG/PRESS-01 | HDPE Woven LDPE laminated Circular Loom | 4500001232 | 30/11/2005 | Sumangal Polymers Pvt. Ltd. |  |  | 29/05/2006, 1st lot within 14.01.06, other lots as per advice of NRL | 1st lot 09/01/06, 100% completed on 05/09/2006
PRC/6192/E/CS,SS,AS Pipes | PIPE 16.0 ASTM A691 GR.11/4CRCL.42-EFW BE | 4500001174 | 14/11/2005 | Bharat Enterprises |  |  | 21/11/2005 | 13/02/2006 | Delay is attributed to vendor. Penalty for delay applied as per order provision
NRL/RO/05-06/17 dtd 11-6-05 | Const.of RO at Umkiang | 4300001882 | 22/12/2005 | M B Enterprise | 2005-09-09 | 2005-09-09 | 26/01/2006 | 26/2/2006 | Modification of alignment of plot had to be done as per recommendation of BRO
OC15000003 | Site Development Works for 60-B Type Quarters at NRL Township(1229). | 4300002264 | 30/01/2006 | M/s. United Enterprise | 2006-11-02 | 2006-11-02 | 31/05/2006 | 14/09/2006 | Road carpeting work could not be taken up due to bad weather condition
NRL/MECH/06/DJD/270 | Mechanical Maintenance Contract for Process Units, Offsites, CPP & Utilities (1219) | 4300002139 | 18/1/2006 | M/s North East Engineering & Construction |  |  | 17/1/2007 | 15/11/2006 | Contract closed
LC05000017 | Neutralising Amine for CDU / VDU | 5500000005 | 23/02/2006 | M/s Ondeo Nalco India Ltd | 2006-10-03 | 28/02/2006 | 15/09/2006 | 16/09/2006 | Reasons attributable to vendor. LD amount as applicable was deducted.
NRL/RO/05-06-36 | RO construction Adabari | 4300002300 | 02//06/06 | BD Enterprise | 28/2/2006 | 28/2/2006 | 100 days from date of handing over of site | 28/3/2007 | Construction was delayed due to non-shifting of existing buildings.
NRL/RO/05-06-36 | RO Construction at Shillong City-2 | 4300002336 | 2006-07-02 | North East Engineering & Associates | 2006-09-03 | 2006-09-03 | 100 days from date of handing over of site | completed | Site was not cleared for construction.
IOTL-NR/NRL/RO/05-06/03 | RO Construction at Tilhar in UP | 4300002347 | 2006-09-02 | Anuj Engineering | 13/12/2005 | 13/12/2005 | 100 days from date of handing over of site | 18/6/2006 | Trees in approach for which NOC was not available.
IOTL-NR/NRL/RO/05-06/01 | RO Construction at Sidhauli in (UP) | 4300002485 | 15/2/2006 | R.K. Auto Service | 17/12/2005 | 17/12/2005 | 100 days from date of handing over of site | 20/5/2006 | Modification in approach and building size etc.
IOTL-NR/NRL/RO/05-06/05 | RO Construction at Kichha in (UA) | 4300002548 | 17/2/2006 | Anuj Engineering | 16/12/2005 | 16/12/2005 | 100 days from date of handing over of site | 2006-04-06 | Discrepancies in plot size sorted out by local authority, HT line was passing through tank locations, tanks shifted on 4.3.2006
IOTL-NR/NRL/RO/05-06/02 | RO Construction at Ucholia | 4300002571 | 21/2/2006 | Evershine Engineering | 2006-07-01 | 2006-07-01 | 100 days from date of handing over of site | 2007-05-04 | Local authority stopped the work many times. Being pond area water logging hampered the work for more than two months.
IOTL-NR/NRL/RO/05-06/08 | RO Construction at Varanasi City in UP | 4300002576 | 21/2/2006 | R.K. Auto Service | 13/01/2006 | 13/01/2006 | 100 days from date of handing over of site | 20/05/2006 | Site was not fully cleared by dealer. There were mango trees in the plot area and local authority stopped work time and again for want of NOC from Development authority.
NRL/RO/05-06/021 | RO Construction at Dimapur NH 39 | 4300002589 | 23/02/2006 | Bidyutalay | 2006-12-03 | 2006-12-03 | 100 days from date of handing over of site | completed | Various site hindrances related to land development, import of construction materials & skilled manpower from Assam, local disturbances in Nagaland
NRL/RO/05-06/021 | RO Construction at Tinsukia | 4300002590 | 23/02/2006 | M B Enterprise | 23/02/2006 | 23/02/2006 | 100 days from date of handing over of site | 29/03/2007 | Modification of driveway from bituminous to paver block had to be done, law & order situation caused stoppage of work at regular intervals
NRL/RO/05-06/021 | RO Construction at Dibrugarh | 4300002594 | 23/02/2006 | Bright Construction Co. | 2006-08-02 | 2006-08-02 | 100 days from date of handing over of site | 23/01/2007 | Construction delayed due to non-shifting of existing buildings, ASEB overhead line, modification required for const of canopy foundation, law & order problem
EIL's tender MA/ICB/6612-00-UP-MR6010/1001 | Carbon Steel Plates | 4500001455 | 17/2/2006 | M/s Essar Steel Limited, M/s SAIL |  |  | 2006-09-05 | 24/04/2007 | Delay is attributed to vendor. Penalty for delay applied as per order provision.
RRFQ/003936 | H2S absoption Catalyst , Type:HTZ-3 | 4500001426 | 2006-06-02 | Haldor Topsoe International A/S |  |  | 8 weeks from LC | 21/04/2006 | Not applicable
NRL/MECH/06/DJD/281 | Operation & Mainteannce of NRL Owned Cranes/Equipments (1332) | 4300002979 | 31/3/2006 | M/s Nishan Enterprise |  |  | 1 (One) Year from the date of handing over the site | 31/3/2007 | Contract closed
LC-10000016/JBS | TMT Bar | 4500001537 | 2006-08-03 | M/s. Seel Authority Of Idia Ltd. |  |  | 30/04/2006 | 2006-09-04 | Not applicable
OC-10000023/JBS | OP Cement | 4500001546 | 2006-10-03 | M/s. Cement Corporation of India Ltd |  |  | 2006-10-06 | 29/06/2006 | Vendor supplied the material as per requirement raised from time to time
LC-10000017/JBS | Mech. Seal | 4500001626 | 25/03/2006 | M/s. Eagle Poonawalla Industry Ltd |  |  | 2006-07-08 | 29/05/2006 | Not applicable
LC15000002 | Acoustic Treatment and Air Conditioning system of Kaliyani Club at NRL Township | 4300002632 | 2006-01-03 | M/s Lloyd Insulations (India) Ltd. | 2006-01-03 | 16/03/2006 | 29/05/2006 | 31/07/2006 | Rectification of existing false ceiling, non completion of machine room
OC15000004 | Construction of Overhead RCC Tank at NRL Township(1228). | 4300002970 | 31/3/2006 | M/s. L.C.Gogoi | 2006-10-04 | 2006-10-04 | 23/07/2006 | 28/05/2007 | Encountering soft rock below foundation, bad weather condition, outside labourers left site for local disturbance
Not Applicable (Power sanction was obtained from WBSEB) | Power Supply for Siliguri Marketing Terminal | Agreement between WBSEB & NRL | 19/01/2005 | M/s West Bengal State Electricity Board | 19/01/2005 | 19/01/2005 | NA | 2006-07-01 | Delay in overall synchronizing of the system
EIL's tender MA-6612-00-LL-MR-4010/1002 | Rail / Road Loading Arms for Siliguri Marketing Terminal Project | LOI NRL/6612/SMTP-RAIL/GSG/LOI | 10/3/06 | M/s Associate Engineers | 24/08/2006 | 24/08/2006 | 2006-12-09 | 20.06.2007 | Delay is attributed to vendor. Penalty for delay applied as per order provision
EIL's tender MA/6612-61-PA-MR-5010/0001 | Centrifugal Horizontal Pumps (Special Purpose Process) ( total 7 items) for Siliguri Marketing Terminal Project | LOI dtd. November 14, 2005 (order no. 4500001558 on M/s Kirloskar Ebara for item 1,3,7 and order no. 4500001576 on M/s Flowserve India for item 2,4,5,6) | 14/03/2006, 20/03/2006 respectively. | 4500001558 on M/s Kirloskar Ebara Pumps Ltd. and 4500001576 on M/s Flowserve India Controls Pvt. Ltd. | 14/03/2006 20/03/2006 respectively | 14/03/2006 20/03/2006 respectively | 13/6/2006, 13/8/2006 respectively | 16/10/2006 22/01/2007 respectively | Delay is attributed to vendor. Penalty for delay applied as per order provision
Not Applicable* | Dispensers | 4500001643 | 30/03/2006 | M/s Glibarco Veeder RootAsia Pte Ltd, Singapore | Date of receipt of LC | 24 weeks from date of receipt of LC | 31/05/2005 | 31/05/2005 | Not applicable
NRL/RO/05-06/037 | RO Construction: Gogamukh | 4300003122 | 2006-06-04 | Hazarika & Co. | 25/04/2006 | 25/04/2006 | 100 days from date of handing over of site | 21/09/2006 | Driveway topping was scheduled after 6 months by NRL as land filling & development was done very recently.
RRFQ/004239 | Supply of Cetane Improver for Euro-III HSD | 4500001682 | 2006-12-04 | Noble Explochem Ltd., Nagpur | 22/04/2006 | 19/04/2006 | 15/10/2006 | 2007-01-04 | Reasons attributable to vendor. LD amount as applicable was deducted.
LC07000017 | Spares for Control valves on PSA Skid in Hydrogen Plant. | 4500001712 | 19/04/2006 | UOP N.V., Belgium |  |  | 16 weeks after Order and L/C. | 2006-08-11 | Not applicable
RRFQ/003933/JBS | Supply of ICP-AES (Inductivety Coupled Plasma-Atomic Emission Spectrophotometer) for Laboratory | 4500001652 | 2006-01-04 | Parkin Rlmer Singapore PTE Ltd |  |  | 2007-03-02 | 2007-03-02 | Not applicable
LC10000034/JBS | TMT Bars(16 mm & 20 mm ) for Township Works at NRL. | 4500001833 & 4500001835 | 29/05/2006 | M/s. Steel Authority of India Ltd & M/s. Tata Iron & Steel Co. Ltd. |  |  | 13/06/2006 | 13/06/2006 | Not applicable
NRL/RO/05-06/38 | Construction of RO in Naharlagun | 4300003948 | 15/06/2006 | Hazarika & Co. | 2006-01-08 | 2006-01-08 | 100 days from date of handing over of site | 15/05/2007 | Location in landslide affected area. Almost all construction material had to be imported from Assam. Arunachal is Innerline permit area, labour movement restricted
NRL/RO/05-06/26 | Construction of RO in Thoubal | 4300003949 | 15/6/2006 | Hazarika & Co. | 15/06/2006 | 15/06/2006 | 100 days from date of handing over of site | 2007-10-02 | Work progress affected due to law & order situation and construction material availability
EIL's DPS/ICB/6612-00-WP-MR-3010/1003 | Motor Operated Valves for Siliguri Mktg. Terminal Project and Numaligarh Despatch Terminal. | NRL/6612/SMTP-010/LOI dt. 09.06.2006 | 2006-09-06 | Audco India Ltd. Chennai | 24/10/2006 | 24/10/2006 | 10 months from date of LOI. | 27/03/2007 | Not applicable
IOTL-NR/NRL/RO/05-06/04 | New RO of NRL at Bareilly city (UP) | 4300004326 | 14/7/2006 | Agarwal Construction | 29/05/2006 | 29/05/2006 | 100 days from date of handing over of site | 14/11/2006 | Hindrances in building foundation as plot was not in right angled corner, PWD authority also stopped the work time and again for culvert in front of plot
PC01000060 | Spares for Elevated Flare | 4500001964 | 31/7/2006 | M/s Airoil Flaregas (India) Pvt. Ltd. |  |  | 2007-07-02 |  | Material recd with minor damage in 1 part
LC07000009 | Supply of Gas Compressor Spares. | 4500001958 | 2006-07-07 | M/s Nuovo Pignone, Italy |  |  | 17 weeks after Order and L/C. | 23/02/2007 | LC dated 02/08/2006, delay by vendor in second shipment
PC01000044 | Supply of spares for KBL Pumps. | 4500002117 | 25/8/2006 | Kirloskar Brothers Ltd. |  |  | 16/3/2007 | TG 25308 dtd. 06/11/2006 through ABC/TG-23410 dtd. 5.1.07 | Not applicable
Not applicable. | Supply of OP Cement (33 Grade) | 4500002037 | 2006-05-08 | M/s. Cement Corporation of India Ltd, Guwahati. |  |  | 31/12/2006 | 29/12/2006 | Not applicable
LC11000033 | Procurement of desktop PC's. | 4500002243 | 27/9/2006 | HCL Infosystems Ltd. |  |  | 13/11/2006 | 22/11/2006 | PR imposed on vendor
LC/11000037 | Hardware for disaster recovery | 4500002318 | 19/10/2006 | M/s PCS Technology Ltd. |  |  | 21/12/2006 | 2007-12-04 | PR imposed on vendor
PSMM-9379-7001-NRL-06-06 dated 08.02.2006. | Procurement of Control Valves for NG Utilization Project. | 4500002262-JBS | 2006-03-10 | M/s. MIL Controls Ltd. | 2006-03-10 | 2006-03-10 | 2007-03-04 | 30/05/2007 | Due to delay in receipt of approved drawings from PMC
PSMM-9379-7001-NRL-06-06 dated 08.02.2006. | Procurement of Control Valves for NG Utilization Project. | 4500002262-JBS | 2006-03-10 | M/s. MIL Controls Ltd. | 2006-03-10 | 2006-03-10 | 2007-03-04 | 30/05/2007 | Vendor's request for delivery extension is under consideration
PC07000050 (RFQ No. 6000001011) | Bucket Assembly, Nozzle Assembly and Shroud Assembly for Gas Turbines of CPP. | 4500002365 | 2006-02-11 | M/s BHEL-GE Gas Turbine Services Ltd., Secunderabad | NA |  | 2007-12-03 | completed | 100% supply made on 04 - Jan - 2007 on FOB basis.
LC01000007 | Supply and Installation of Supercritical Fluid Chromatograph (D-5186). | 4500002404 | 2006-11-11 | M/s AC Analytical Controls BV, The Netherlands |  |  | 6 to 8 weeks from order and LC | 13/05/2007, LC dtd. 13.4.2007 | Not applicable
LC01000107 | Spares for KEPL make pumps | 4500002377 | 2006-06-11 | Kirloskar Ebara Pumps Limited, Pune |  |  | 28/05/2007 | LR ref: B 665001 dtd. 31.01.2007 thru ARC | Not applicable
PC01000073 | Spares for Air Compressor | 4500002435 | 22/11/2006 | Ingersoll Rand India Ltd. |  |  | 2007-07-03 | LR ref: CN No: 133205 dtd. 30/12/06 thru ARC | Not applicable
LC31000038 | Supply of AUTOMATIC SERVO VOLTAGE STABILISER , Mak | 4500002440 | 24/11/2006 | Assam Electricals | 24/11/2006 | 24/11/2006 | 3 to 4 months from date of Work Order | All materials recd. At Guwahati ware house on 28/02/2007 and despatched to respective locations | Not applicable
LC10000059 | TMT Bar, Procurement | 4500002526 | 19/12/2006 | Kamdhenu Ispat Ltd. |  |  | 27/12/2006 | 27/02/2007 | Delay is attributed to vendor, penalty is applicable as per order
6000000710 | Supply of Reforming Catalyst; Type (R67-7H). | 4500002484 | 2006-11-12 | Haldor Topsoe A/S |  |  | 5/2/2007, 8 weeks from order & LC | 23/03/2007, LC dtd. 21/02/2007 | Not applicable
PC07000058 | Supply of MT, LT and Hydrogenator Catalyst for H2U of NRL. | 4500002513 | 15/12/2006 | Haldor Topsoe A/S |  |  | 10 weeks from order & LC | 2007-12-04 | Not applicable
Tendering by M/s Bharat Petroleum Corporation Ltd. | Canopy & signage Job - Hasimara | 4300006471 | 2007-01-02 | A R Rural Electricals | 16/01/2007 | 16/01/2007 | Job awarded by BPCL | Within schedule time | Not applicable
LC10000073/PB1 | Supply of TMT Bars at NRL. | 4500002945-PB1 | 22/03/2007 | M/s. Brahmaputra Iron & Steel Co Ltd. |  |  | 22/04/2007 | 27/04/2007 | Delay is attributable to vendor. Penalty is applicable as per provision of the order
Tendering done by BPCL | CONSTRUCTION OF SALES BUILDING- MANIGUDA | 4300006845 | 2007-06-03 | Roy Chowdhury & Co |  |  | 17/01/2007 | Within schedule | Not applicable
Tendering done by BPCL | Canopy & Signage - Patna By Pass | 4300007080 | 23/3/2007 | A R Rural Electricals |  |  | 2007-06-03 | Within schedule time | Not applicable
LC05000037 | Supply of Cetane Improver for Euro-III HSD | 4500003003 | 2007-02-04 | M/s Noble Explochem Ltd, Nagpur |  |  | Requirement is for 1 year consumption with delivery in staggered manner as per intimation from NRL. CDD for 1st lot of 45 MT was on 23-04-07 as given in order. |  | PO is cancelled as the vendor regretted to supply the item against the PO. PR is refloated vide LC05000062 dtd. 12.06.2007.
Not Applicable | Purchase of RO Land at Mohali | 4300007735 | 21/5/2007 | Sh.Dalmir Singh | N/A | N/A | Not Applicable |  | Sale deed registered & payment made on 24/05/2007