## Upto Nov 07
Project Completion Status
Up to November 30, 2007.
Sl. | Tender Number | Item / Nature of work | Contract Number | Contract date | Name of contractor | Scheduled start date | Actual date of start of work | Scheduled completion date | Actual completion date | Reasons for delay
1 | NRL/MT/06/251 | Bagging Works | 4300000855 | 17/09/2005 | Selectromech | 18/09/2005 | 18/09/2005 | 17/09/2006 | 17/09/2006
2 | OC19000001 | Road Repairing at Refinery & NRMT (Phase-III) (1098) | 4300002949 | 28/3/2006 | M/s M P Agarwalla | 28/3/2006 | 2006-12-04 | 6 (Six) months from the date of handing over the site | 2006-07-11 | Rain & bandhs
3 | NRL/COMM(PUR)/HSD-Trans/04 | HSD Transportation through Waterways from Ex-Silghat to Budge-Budge. | LOI dtd. April 23, 2005 / 4300002645 | 23/04/05 and 03/02/06 | M/s Vivada Inland Waterways Limited, Kolkata | 23/04/2005 | 17/06/2005 | 23/04/2006 | 2006-11-04
4 | OC19000004 | Gr. A- Painting Works at ETP, DM Plant & Cooling Tower. Gr.-B.- Maintenance Contracts for Industrial painting for Two Years | 4300003501 | 2006-11-05 | M/s R.K. Sharma | 2006-11-05 | 2006-01-06 | 1. 7(Seven) Months for Group-A. 2. 2(Two) years for Group-B. | Group-A: 31.12.2006Group-B: In progress. | Not applicable
5 | PSMM-9379-300-NRL-01-05/25.01floated by PMC, M/s. PDIL. | Procurement of 2 Nos. Knock Out Drums(KOD) for NG Project. | LOI ref: NRL/9379/01/FOA-1 & NRL/9379/01/FOA-2 | 31/5/2006 | M/s. Indus Projects Ltd & M/s. R.D. Engineers. | 31/5/2006 | 31/5/2006 | 31/11/06 | 30/4/07 M/s Indus Projects, 29/8/07 M/s RD Engineers | Due to delay in submission & approval of drawings from PMC.
6 | 6000000011 | Hiring of NRL's identified shore tank for storing imported MTBE at Budge Budge, custom clearance, arranging surveyor, sealing of tank lorries, sampling etc. At Budge Budge | 4300004056 (repeat order of the orginal order 4300000451 | 23/6/2006 | TKM Transport Management Services | 26/4/2006 | 26/4/2006 | 31/12/2006 | 25/10/2006 | NA
7 | OC21000007 | Handling, shifting, bagging & loading of CPC in CCU (1450) | 4300004878 | 2006-09-09 | M K Agarwalla | 18/9/2006 | 18/9/2006 | 17/9/2007 | 17/9/2007 | NA
8 | "Expression of Interest" invited through press. Four parties showed interest Their documents were reviewed. Limited tender (in 2 bid) NRL/COMM(PUR)/HSD-Trans/04 dtd. 4th Nov, 04 was floated to them. Last date (extended) of tender receipt was 7th Dec. 04. Single offer from M/s Vivada Inland Waterways Limited, Kolkata was received. After techno-commercial discussion a Contract was signed on 8th June 05 at negotiated rates. | HSD Transportation through Waterways from Ex-Silghat to Budge-Budge. | Contract of Affreightment for Movement of Bulk Petroleum Products by Barge (signed on 08 Nov. 06). Regularised in ERP system by WO 4300005589 | 15/11/2006 | M/s Vivada Inland Waterways Limited, Kolkata | 2007-01-07 | 2006-01-08 | 31/07/2007 | 31/07/2007 | NA
9 | OC1000054/JBS | Mechanical Works for NSPL Despatch facilities at NRL. | 4300006001 | 21/12/2006 | North East Engg & Construction. | 22/12/06 | 2007-05-01 | 18/03/2007 | 30/9/07 | Due to non -receipt of materials in time.
10 | OC19000012 | Brick Pitching at Pipe Track area at NRM | 4300005914 | 2006-12-12 | Ganesh Tamuli | 2006-12-12 | 20/01/2007 | 09 (Nine) Months to be reckoned from the date of handing over of site. | 31/10/07 | Rain & bandhs
11 | OC19000012 | Brick Pitching at Pipe Track area at NRM | 4300005915 | 2006-12-12 | Dee Pee Engineering | 2006-12-12 | 22/01/2007 | 09 (Nine) Months to be reckoned from the date of handing over of site. | 31/10/07 | Rain & bandhs
12 | Tendering done by BPCL | METHYL TERTIARY BUTYLE ETHER | 4500002449 | 2006-01-12 | Petronas Mitco | 29/11/2006 | 29/11/2006 | 26/12/06 | MTBE parcel despatched vide Bill of Lading dt. 29/11/06
13 | Not available | PYROLYSIS GASOLINE | 4500002459 | 2006-02-12 | Haldia Petrochemicals Limited | 2006-01-12 | 2006-01-12 | 15/12/06 | 15/12/06 | Short closed and completed
14 | Not available | PYROLYSIS GASOLINE | 4500002536 | 21/12/2006 | Haldia Petrochemicals Limited | 16/12/2006 | 16/12/2006 | 31/12/06 | 31/12/06 | Short closed and completed
15 | Not available | RAIL FREIGHT AS PER RR-Dec'06 | 4300005880 | 2006-01-12 | FA &CAO , NF RAILWAY , MALIGAON | 2006-01-12 | 2006-01-12 | 31/12/06 | 31/12/06
16 | Term.MTBE.06/06 of BPC IT Division | Procurement of first parcel (of three parcels) 2000 MT (+) 5% MT per month on CFR Budge Budge basis | Term.MTBE.06/06 dtd. 28-11-06 (NRL's PO 4500002577) | 2007-03-01 | Saudi Basic Industries Corporation, Saudi Arabia |  | 29/11/2006 | 21/12/2006 | Bill of Lading dt. 21/12/06, invoice dt. 31/12/06
17 |  | Procurement of second parcel (of three parcels) 2000 MT (+) 5% MT per month on CFR Budge Budge basis | Term.MTBE.06/06 dtd. 28-11-06 (NRL's PO 4500002677) | 30/1/2007 |  |  | 22/1/2007 | 31/01/2007 | Bill of Lading dt. 22/1/07, invoice dt. 29/01/07
18 | Not applicable | Procurement of PYROLYSIS GASOLINE | 4500002613 | 2007-09-01 | Haldia Petrochemicals Limited, Kolkata | 2007-01-01 | 2007-01-01 | 15/1/2007 | 15/1/2007 | Short closed and completed
19 | Not applicable | Procurement of PYROLYSIS GASOLINE | 4500002647 | 19/1/2007 | Haldia Petrochemicals Limited, Kolkata | 2007-05-01 | 2007-05-01 | 31/1/2007 | 31/1/2007 | Short closed and completed
20 | OC07000001/ MKD | HDPE bag 50 Kg capacity | 1) 4500002656/MB1 2) 4500002657/MB1 | 22-Jan-2007 for both orders | 1) Sai Surfactants Pvt. Ltd., Kolkata 2) Sumangal Polymers Pvt. Ltd., Kolkata | 22/01/2007 | 24/1/2007 | 15/9/2007 | 15/10/2007 27/09/2007
21 | Not applicable | RAIL FREIGHT AS PER RR-Dec'06 | 4300006198 | 2007-08-01 | FA &CAO , NF RAILWAY , MALIGAON | 2007-01-01 | 2007-01-01 | 31/1/2007 | 31/1/2007
22 | LC10000055-JBS | LT/HT PVC Cables at Numaligarh Refinery Limited | 45000002767 | 20/2/2007 | M/s. KEI Industries Ltd | 20/02/2007 | 20/02/2007 | 30/4/2007 | 2007-05-11 | Initial drum was rejected due to insufficient length
23 | Not Applicable | Procurement of PYROLYSIS GASOLINE | 4500002690 | 2007-01-02 | Haldia Petrochemicals Limited, Kolkata | 2007-01-02 | 2007-01-02 | 15/2/2007 | 15/2/2007 | Short closed and completed
24 | Not Applicable | Procurement of PYROLYSIS GASOLINE | 4500002769 | 20/2/2007 | Haldia Petrochemicals Limited, Kolkata | 16/2/2007 | 16/2/2007 | 28/2/2007 | 28/2/2007 | Short closed and completed
25 | Not Applicable | CRUDE-OIL | 4500002747 | 2007-01-02 | Oil India Limited | 2007-01-02 | 2007-01-02 | 28/2/2007 | 28/2/2007 | Nil
26 | Not Applicable | CRUDE-ONGC | 4500002748 | 2007-01-02 | Oil and Natural Gas Corporation | 2007-01-02 | 2007-01-02 | 28/2/2007 | 28/2/2007 | Nil
27 | Not Applicable | RAIL FREIGHT AS PER RR-Feb'07 | 4300006588 | 2007-01-02 | FA &CAO , NF RAILWAY , MALIGAON | 2007-01-02 | 28/2/2007 | 28/2/2007 | 28/2/2007
28 | LC07000075 | Shore Tank hiring, customs clearance etc. for handling MTBE at Budge Budge | 4300007200 dtd. 31.03.2007 against LOI dtd. February 13, 2007 | 31/3/2007 | Cargo Partners Logistics India Pvt. Ltd., Kolkata | 2007-01-02 | 2007-01-02 | 31/5/2007 | 31/5/2007 | NA
29 | Not Applicable | Procurement of PYROLYSIS GASOLINE | 4500002817 | 2007-05-03 | Haldia Petrochemicals Limited, Kolkata | 2007-01-03 | 2007-01-03 | 15/3/2007 | 15/3/2007 | Short closed and completed
30 | Not Applicable | Procurement of PYROLYSIS GASOLINE | 4500002905 | 17/3/2007 |  | 16/3/2007 | 16/3/2007 | 31/3/2007 | 31/3/2007 | Short closed and completed
31 | Not available | RAIL FREIGHT AS PER RR-March'07 | 4300006784 | 2007-01-03 | FA &CAO , NF RAILWAY , MALIGAON | 2007-01-03 | 2007-01-03 | 31/3/2007 | 31/3/2007
32 | Not Applicable | CRUDE - OIL | 4500002949 | 2007-01-03 | OIL INDIA LIMITED | 2007-01-03 | 2007-01-03 | 31/3/2007 | 31/3/2007 | Nil
33 | Not Applicable | CRUDE - ONGC | 4500002951 | 2007-01-03 | Oil And Natural Gas Corporation | 2007-01-03 | 2007-01-03 | 31/3/2007 | 31/3/2007 | Nil
34 | Not Applicable | Procurement of PYROLYSIS GASOLINE | 4500003005 | 2007-03-04 | Haldia Petrochemicals Limited, Kolkata | 2007-01-04 | 2007-01-04 | 15/4/2007 | 15/4/2007 | NA
35 | Not Applicable | Procurement of PYROLYSIS GASOLINE | 4500003104 | 23/4/2007 | Haldia Petrochemicals Limited, Kolkata | 16/4/2007 | 16/4/2007 | 30/4/2007 | 30/4/2007 | Short closed and completed
36 | Not Applicable | RAIL FREIGHT AS PER RR-April''07 | 4300007492 | 2007-01-04 | FA &CAO , NF RAILWAY , MALIGAON | 2007-01-04 | 2007-01-04 | 30/4/2007 | 30/4/2007 | Short closed and completed
37 | Not Applicable | CRUDE - OIL | 4500003107 | 2007-01-04 | OIL INDIA LIMITED | 2007-01-04 | 2007-01-04 | 30/4/2007 | 30/4/2007 | Nil
38 | Not Applicable | CRUDE - ONGC | 4500003108 | 2007-01-04 | Oil And Natural Gas Corporation | 2007-01-04 | 2007-01-04 | 30/4/2007 | 30/4/2007 | Nil
39 | Not Applicable | Procurement of PYROLYSIS GASOLINE | 4500003168 | 2007-07-05 | Haldia Petrochemicals Limited, Kolkata | 2007-01-05 | 2007-01-05 | 15/05/2007 | 15/5/2007 | Short closed and completed
40 | Not Applicable | Procurement of PYROLYSIS GASOLINE | 4500003201 | 16/5/2007 | Haldia Petrochemicals Limited, Kolkata | 16/5/2007 | 31/5/2007 | 31/05/2007 | 31/5/2007 | Short closed and completed
41 | Not Applicable | RAIL FREIGHT AS PER RR-May''07 | 4300007795 | 2007-01-05 | FA &CAO , NF RAILWAY , MALIGAON | 2007-01-05 | 2007-01-05 | 31/05/2007 | 31/5/2007 | NA
42 | Not Applicable | CRUDE - OIL | 4500003230 | 2007-01-05 | OIL INDIA LIMITED | 2007-01-05 | 2007-01-05 | 31/5/2007 | 31/5/2007 | Nil
43 | Not Applicable | CRUDE - ONGC | 4500003231 | 2007-01-05 | Oil And Natural Gas Corporation | 2007-01-05 | 2007-01-05 | 31/5/2007 | 31/5/2007 | Nil
44 | Not Applicable | RAIL FREIGHT AS PER RR-JUNE'07 | 4300008018 | 2007-01-06 | FA &CAO , NF RAILWAY , MALIGAON | 2007-01-06 | 2007-01-06 | 30/6/2007 | 30/6/2007 | NA
45 | Not Applicable | PYROLYSIS GASOLINE | 4500003284 | 2007-04-06 | Haldia Petrochemicals Limited | 2007-01-06 | 2007-01-06 | 15/6/2007 | 15/6/2007 | Short closed and completed
46 | Not Applicable | CRUDE - OIL | 4500003304 | 2007-01-06 | OIL INDIA LIMITED | 2007-01-06 | 2007-01-06 | 30/6/2007 | 30/6/2007 | Nil
47 |  | CRUDE - ONGC | 4500003306 | 2007-01-06 | Oil And Natural Gas Corporation | 2007-01-06 | 2007-01-06 | 30/6/2007 | 30/6/2007 | Nil
48 | Not Applicable | PYROLYSIS GASOLINE | 4500003372 | 20/6/2007 | Haldia Petrochemicals Limited | 16/6/2007 | 16/6/2007 | 30/6/2007 | 30/6/2007 | Short closed and completed
49 | Not Applicable | PYROLYSIS GASOLINE | 4500003420 | 2007-05-07 | Haldia Petrochemicals Limited | 2007-01-07 | 2007-01-07 | 15/7/2007 | 15/7/2007 | Short closed and completed
50 | Not Applicable | PYROLYSIS GASOLINE | 4500003465 | 19/7/2007 | Haldia Petrochemicals Limited | 16/7/2007 | 16/7/2007 | 31/7/2007 | 31/7/2007 | Short closed and completed
51 | Not Applicable | RAIL FREIGHT AS PER RR-July''07 | 4300008250 | 2007-01-07 | FA &CAO , NF RAILWAY , MALIGAON | 2007-01-07 | 2007-01-07 | 31/7/2007 | 31/7/2007 | NA
52 | Not Applicable | CRUDE - OIL | 4500003447 | 2007-01-07 | OIL INDIA LIMITED | 2007-01-07 | 2007-01-07 | 31/7/2007 | 31/7/2007 | Nil
53 | Not Applicable | CRUDE - OIL | 4500003448 | 2007-01-07 | Oil And Natural Gas Corporation | 2007-01-07 | 2007-01-07 | 31/7/2007 | 31/7/2007 | Nil
54 | Not Applicable | PYROLYSIS GASOLINE | 4500003539 | 2007-03-08 | Haldia Petrochemicals Limited | 2007-01-08 | 2007-01-08 | 15/8/2007 | 15/8/2007 | Short closed and completed
55 | Not Applicable | PYROLYSIS GASOLINE | 4500003596 | 28/8/2007 | Haldia Petrochemicals Limited | 16/8/2007 | 16/8/2007 | 31/8/2007 | 31/8/2007 | Short closed and completed
56 | Not Applicable | CRUDE - OIL | 4500003561 | 2007-01-08 | OIL INDIA LIMITED | 2007-01-08 | 2007-01-08 | 31/8/2007 | 31/8/2007 | Nil
57 | Not Applicable | CRUDE - ONGC | 4500003562 | 2007-01-08 | Oil And Natural Gas Corporation | 2007-01-08 | 2007-01-08 | 31/8/2007 | 31/8/2007 | Nil
58 | Not Applicable | RAIL FREIGHT AS PER RR-Aug''07 | 4300008674 | 2007-01-08 | FA &CAO , NF RAILWAY , MALIGAON | 2007-01-08 | 2007-01-08 | 31/8/2007 | 31/8/2007 | NA
59 | Not Applicable | CRUDE - OIL | 4500003653 | 2007-01-09 | M/s OIL INDIA LIMITED | 2007-01-09 | 2007-01-09 | 30/9/2007 | 30/9/2007 | Nil
60 | Not Applicable | CRUDE - ONGC | 4500003654 | 2007-01-09 | M/s Oil And Natural Gas Corporation | 2007-01-09 | 2007-01-09 | 30/9/2007 | 30/9/2007 | Nil
61 | Not Applicable | RAIL FREIGHT AS PER RR-SEPT'07 | 4300008905 | 2007-01-09 | M/s FA &CAO , NF RAILWAY , MALIGAON | 2007-01-09 | 2007-01-09 | 30/9/2007 | 30/9/2007 | NA
62 | NA | Py-Gas | 4500003789 | 13/10/2007 | Haldia Petrochemicals Limited | 2007-01-10 | 2007-01-10 | 15/10/2007 | 15/10/2007 | Short closed and completed
63 | NA | Py-Gas | 4500003817 | 24/10/2007 | Haldia Petrochemicals Limited | 16/10/2007 | 16/10/2007 | 31/10/2007 | 31/10/2007 | Short closed and completed
64 | Not Applicable | CRUDE - OIL | 4500003763 | 2007-01-10 | OIL INDIA LIMITED | 2007-01-10 | 2007-01-10 | 31/10/2007 | 31/10/2007 | Nil
65 | Not Applicable | Oil And Natural Gas Corporation | 4500003764 | 2007-01-10 | Oil And Natural Gas Corporation | 2007-01-10 | 2007-01-10 | 31/10/2007 | 31/10/2007 | Nil
66 | Not Applicable | RAIL FREIGHT AS PER RR-OCT'07 | 4300009138 | 2007-01-10 | FA &CAO , NF RAILWAY , MALIGAON | 2007-01-10 | 2007-01-10 | 31/10/2007 | 31/10/2007 | NA
67 |  | RAIL FREIGHT AS PER RR-Nov'07 | 4300009336 | 2007-01-11 | FA &CAO , NF RAILWAY , MALIGAON | 2007-01-11 | 2007-01-11 | 30/11/2007 | 30/11/2007 | NA
68 |  | CRUDE - OIL | 4500003869 | 2007-01-11 | OIL INDIA LIMITED | 2007-01-11 | 2007-01-11 | 30/11/2007 | 30/11/2007 | Nil
69 |  | CRUDE - ONGC | 4500003870 | 2007-01-11 | Oil And Natural Gas Corporation | 2007-01-11 | 2007-01-11 | 30/11/2007 | 30/11/2007 | Nil
70 |  | PYROLYSIS GASOLINE | 4500003885 | 2007-12-11 | Haldia Petrochemicals Limited | 2007-01-11 | 2007-01-11 | 15/11/2007 | 15/11/2007 | Short closed and completed
71 |  | PYROLYSIS GASOLINE | 4500003967 | 27/11/2007 | Haldia Petrochemicals Limited | 16/11/2007 | 16/11/2007 | 30/11/2007 | 30/11/2007 | Short closed and completed